SINGLEBIT · FOUNDER'S OFFICE

Mobile App

Onboarding Playbook

End-to-End Operating Document  ·  Idea to Shipped

Version 1.0  ·  April 2026  ·  Internal Use Only

Authored by the Founder's Office  ·  Not for external distribution

# Introduction

This playbook is the single source of truth for how I take a founder from their first email to a live mobile app. It covers every stage of the engagement lifecycle and exists so that quality is consistent, client experience is predictable, and nothing falls through the gaps. It is not a guide to read once and file away. It is the process I follow on every project.

Who this is for: everyone in the Founder's Office, engineering leads, growth leads, and any team member brought onto a project. Leadership uses it to review process health. New team members use it to get up to speed without needing to be walked through everything manually.

Scope: This version covers mobile app projects (iOS, Android, or cross-platform) where the founder starts with an idea only. Adjustments for web-only or AI-only projects are noted where they apply.

Recommended engagement model: Hybrid. Fixed-price for the MVP build, with an optional monthly retainer post-launch for the Optimise phase. Payment milestones: 40% on contract signing, 30% on design approval, 30% on final delivery.

# Table of Contents

| Stage 1 | Inbound and First Response |
| --- | --- |
| Stage 2 | Qualification |
| Stage 3 | Discovery Call |
| Stage 4 | Scoping |
| Stage 5 | Proposal |
| Stage 6 | Onboarding |
| Stage 7 | Design Sprint |
| Stage 8 | Development |
| Stage 9 | QA, UAT and Client Review |
| Stage 10 | Delivery, Handoff and Post-Launch |
| Appendix A | Process Flow Diagram |
| Appendix B | Timeline Reference |
| Appendix C | Communication Cadence |

STAGE 1 INBOUND AND FIRST RESPONSE First contact to first reply within 2 hours.

| Objective | Capture every incoming lead professionally and quickly. The first response sets the tone for the entire relationship. |
| --- | --- |
| Steps | - Receive inquiry at hq@singlebit.xyz. Website contact form submissions are auto-routed here. - Read the email fully. Note: idea description, urgency signals, any budget signals, founder background if mentioned. - Log the lead in Notion CRM within 30 minutes: Name, Email, Idea Summary, Date Received, Source Channel. - Send the First Response using the Standard Template within 2 hours during working hours (9am to 7pm IST). The template acknowledges the idea, sets expectations for next steps, and asks one clarifying question if the idea is unclear. - Mark lead status in Notion as "Responded - Awaiting Reply". - Set a 3-business-day follow-up reminder in Notion. If no reply, send one gentle follow-up. If still no reply after 5 days, mark status as "Cold" and archive. |
| Inputs | Incoming email or website contact form submission |
| Outputs | Lead logged in Notion CRM, first response sent, follow-up reminder set |
| Ownership | Abhiraj Sakargaye |
| Tools | Gmail, Notion |

STAGE 2 QUALIFICATION Decide if this lead is worth a discovery call before investing time.

| Objective | Filter for genuine fit. Not every inquiry is a project. Running discovery calls on unqualified leads wastes time for both sides. |
| --- | --- |
| Steps | - Once the founder replies, review their response and the Notion lead record. - Run the Qualification Checklist against 5 signals: - Idea clarity: can they describe what they want to build in two sentences? - Budget readiness: any signal of funding, revenue, or personal investment? - Decision authority: are they the decision-maker, or do they need approvals from others? - Timeline pressure: is there urgency with a real, stated reason? - Scope realism: is the MVP scope reasonable, or is it five different products in one? - Score: 3 or more green signals means proceed to a discovery call. - If qualified: send a calendar link for a 30 to 45 minute discovery call with a brief note on what to expect and what to prepare. - If not qualified: send a polite decline with an honest, specific reason. No ghosting. - Update Notion status: "Discovery Call Scheduled" or "Not a Fit". |
| Inputs | Founder reply, lead record in Notion, Qualification Checklist |
| Outputs | Discovery call scheduled or polite decline sent. Notion status updated. |
| Ownership | Abhiraj Sakargaye |
| Tools | Notion, Gmail, Google Calendar |

STAGE 3 DISCOVERY CALL Understand the real problem, not just the stated one.

| Objective | Leave the call with enough clarity to scope the work accurately. The problem as first described is almost always different from the actual problem. |
| --- | --- |
| Steps | - Send a prep note to the founder 24 hours before the call: what to bring (existing docs, competitor references, design inspiration), what the call will cover. - Conduct the 30 to 45 minute call. Abhiraj leads. Naman joins for technically complex projects. - Work through the Discovery Question Framework: - What problem does this app solve, and who has it most acutely? - Who is the first user? Describe a day in their life without this app. - What does success look like at 6 months and 12 months? - Have you tried any manual version of this? What happened? - What platforms: iOS, Android, or both? - What is your go-live deadline, and why does that date matter? - Do you have existing brand assets, design work, or technical foundations? - What is your rough budget range for this project? - Log notes in Notion during or immediately after the call. Never rely on memory. - Write a one-page Discovery Summary in Notion within 24 hours: Problem Statement, Target User, Core Features (rough), Constraints, Next Step. - Send the founder a follow-up email within 24 hours summarising what was discussed and confirming next steps. |
| Inputs | Scheduled call, Discovery Question Framework, lead record in Notion |
| Outputs | Discovery notes, Problem Statement, Discovery Summary in Notion, follow-up email sent to founder |
| Ownership | Abhiraj Sakargaye (leads call), Naman Barkiya (technical input for complex projects). Both sign off on Discovery Summary. |
| Tools | Google Meet, Notion, Gmail, Loom (optional for async follow-up clips) |

STAGE 4 SCOPING Translate discovery into a concrete, actionable plan.

| Objective | Define exactly what we are building, what we are not, and in what order. This document becomes the source of truth for every decision made in the project. |
| --- | --- |
| Steps | - Naman reviews the Discovery Summary and produces a technical architecture map: stack choice, data model sketch, third-party API dependencies, platform targets. - Define the MVP Feature Set. List every feature discussed. Tag each as: - IN: must ship in the MVP - OUT: post-launch, not in this engagement - NICE: include only if time and budget allow after IN features are complete - Write the Scope Document in Notion. It must include: problem statement, target platforms, tech stack, tagged feature list, sprint breakdown (Sprint 1 = foundation, Sprint 2 = core features, Sprint 3 = secondary features, Sprint 4 = QA and polish), preliminary timeline range, and an explicit out-of-scope list. - Abhiraj reviews the Scope Document for business alignment: is the feature set commercially logical, does the sprint order match client priorities, are any assumptions about the founder's business incorrect? - Both Naman and Abhiraj sign off on the Scope Document before moving to proposal. Disagreements are resolved here, not after the proposal is sent. |
| Inputs | Discovery Summary, Naman's technical architecture assessment |
| Outputs | Scope Document, Sprint Map, Preliminary Timeline Range, co-founder sign-off recorded in Notion |
| Ownership | Naman Barkiya (technical scoping), Abhiraj Sakargaye (business review and sign-off) |
| Tools | Notion, Figma (early architecture sketches if needed) |

STAGE 5 PROPOSAL Tailored offer with no hidden costs, sent within 3 to 5 days of the discovery call.

| Objective | Give the founder everything they need to make a clear decision. No vague pricing, no open scope, no surprises after signing. |
| --- | --- |
| Steps | - Abhiraj writes the proposal using the Scope Document as the foundation. Use the Proposal Template in Notion. - The proposal must include all of the following: - One-paragraph summary of what we understand the founder is building and why - What we are building: feature list in plain language, no technical jargon - What we are NOT building: explicitly listed to prevent scope creep - Tech stack and target platforms - Sprint structure and weekly delivery commitment - Timeline range with named conditions (see Appendix B) - Total fixed price and payment milestones: 40% on signing, 30% at design approval, 30% on delivery - Change order process: what happens if scope changes mid-project - Naman reviews the proposal for technical accuracy before it is sent. - Send the proposal as a Notion page link or clean PDF within 3 to 5 business days of the discovery call. - Follow up once if no response within 3 business days. A single short message, not a chase. - If the founder negotiates: revisit the Scope Document together. Do not discount price without removing scope. Every price reduction requires a scope reduction. - Update Notion status: "Proposal Sent", "Negotiating", or "Closed Won / Lost". |
| Inputs | Scope Document, internal pricing calculator |
| Outputs | Proposal sent to founder. Notion status updated. |
| Ownership | Abhiraj Sakargaye (writes and sends), Naman Barkiya (reviews technical accuracy) |
| Tools | Notion, Gmail |

STAGE 6 ONBOARDING NDA, contract, payment, workspace, kick-off. Nothing starts before all of this is complete.

| Objective | Formalise the engagement completely before any design or development work begins. No exceptions. |
| --- | --- |
| Steps | - Once the founder approves the proposal verbally or in writing, send the NDA for signature. Use the standard SingleBit NDA unless the founder has their own version. - Send the Service Agreement and Statement of Work (SOW) for signature. The SOW mirrors the proposal scope word for word. - Collect the first payment: 40% of the project total. No work starts until this payment clears. - Create the project workspace in Notion: Project Brief, Scope Document, Sprint Tracker, Client Review Log, Assets Folder, and Credentials Vault. - Create the project Slack channel. Naming format: "SB - [Client Name] - [App Name]". Invite the founder. Send a welcome message explaining what goes in Slack vs. Notion and response time expectations. - Conduct the 60-minute Kick-off Call: - Walk through the scope and sprint plan together. Confirm the founder understands what is IN and what is OUT. - Set communication expectations: 4-hour Slack response during working hours, 48-hour turnaround on all review requests, Friday demos every week without exception. - Confirm the review contact: who on the founder's side has final approval authority? - Agree on Sprint 1 goals and start date (the following Monday). - Log kick-off decisions in Notion. Sprint 1 starts the following Monday. |
| Inputs | Signed proposal, NDA template, SOW template, first payment received |
| Outputs | Signed NDA, signed SOW, active Notion workspace, active Slack channel, kick-off call completed, Sprint 1 start date confirmed |
| Ownership | Abhiraj Sakargaye (contracts, payment, client communication), Naman Barkiya (Notion workspace setup, kick-off technical section) |
| Tools | Notion, Slack, Gmail, Google Meet, DocuSign or PDF signing tool |

STAGE 7 DESIGN SPRINT Blank canvas to approved hi-fi screens before a single line of code is written.

| Objective | Resolve every product and UX question in design before engineering begins. Design is the cheapest place to catch problems. |
| --- | --- |
| Steps | - Week 1: Produce low-fidelity wireframes for all core screens in Figma. Focus entirely on structure and user flow. No colours, no brand decisions at this stage. - Share wireframes with the founder. Set a 48-hour feedback window. Use the structured feedback format in Notion: What works, What does not work, What is missing. - Client Review Round 1 (Wireframes): Incorporate wireframe feedback. Confirm every flow is correct before moving to hi-fi. A structural change caught here costs a fraction of what it costs at hi-fi or in development. - Weeks 2 to 3: Produce high-fidelity screens in Figma. Apply brand (colours, typography, component library). Deliver: onboarding flow, home screen, all core feature screens, empty states, and error states. - Share hi-fi designs with the founder. 48-hour feedback window. Structured feedback in Notion. - Client Review Round 2 (Hi-Fi): Incorporate final design feedback. This is the last design review round included in scope. Any further rounds are billed as change orders. - Collect written design approval from the founder (a Slack message is sufficient). Collect the 30% payment milestone at design approval. - Hand designs to engineering: share the annotated Figma file in Notion. Naman reviews for implementation notes and flags anything needing a technical adjustment. |
| Client Review Rounds | 2 rounds included: Round 1 on wireframes, Round 2 on hi-fi. Additional rounds are change orders. |
| Inputs | Brand assets (if any), competitor references from discovery, Scope Document |
| Outputs | Approved wireframes, approved hi-fi Figma file, annotated design handoff in Notion, payment milestone 2 collected |
| Ownership | Naman Barkiya or Adarsh Pandey (design execution), Abhiraj Sakargaye (client communication and approval collection) |
| Tools | Figma, Notion, Slack |

STAGE 8 DEVELOPMENT Weekly sprints, live staging from day one, Friday demos every week.

| Objective | Build the app in focused, time-boxed sprints. Ship visible, testable progress every Friday. Surface blockers in days, not weeks. |
| --- | --- |
| Sprint Structure | - Sprint 1 (Weeks 4 to 5): Foundation. Repository setup, authentication, navigation shell, design system in code. - Sprint 2 (Weeks 6 to 8): Core Features. Primary screens live, API connections wired, database structure in place. - Sprint 3 (Weeks 9 to 11): Secondary Features. Supporting screens, push notifications, admin panel or backend dashboard if required. - Sprint 4 (Weeks 12 to 13): QA and Polish. Bug fixes, performance tuning, edge case handling, final visual alignment to approved designs. Timeline ranges vary by project complexity. See Appendix B. |
| Weekly Rhythm | - Monday: Sprint kickoff note in Slack from Naman. Lists what gets built this week and any dependencies the founder needs to be aware of. - Wednesday: Async mid-week update in Slack if anything is blocked or a founder decision is needed. Not required if the sprint is on track. - Friday: 30-minute live demo on Google Meet, or a Loom video walkthrough if the founder is unavailable. Founder reviews and logs feedback in Notion by Monday. - Monday next: Feedback from the Friday demo is captured in the Notion Sprint Review Log. Sprint plan is adjusted only if there is a valid reason. |
| Dev Milestones | - M1: Auth and navigation shell complete. End of Sprint 1. Founder sign-off required before Sprint 2 begins. - M2: Core features functional on staging. Mid-Sprint 2. Internal sign-off only. - M3: Full feature set on staging. End of Sprint 3. Founder sign-off required before QA sprint begins. - M4: QA-clean build ready for UAT. End of Sprint 4. Internal sign-off before UAT is handed to the founder. Staging URL is live from Sprint 1 Day 1. The founder can access it at any time. |
| Change Requests | Any scope change request from the founder is raised as a formal Change Request in Notion. Abhiraj assesses impact on timeline and cost before accepting. No scope additions are absorbed silently into the sprint. |
| Inputs | Approved Figma designs, Scope Document, sprint plan in Notion |
| Outputs | Live staging URL, sprint demo recordings in Notion, milestone sign-offs, Change Request log |
| Ownership | Naman Barkiya (engineering lead, architecture decisions), Adarsh Pandey (engineering execution), Abhiraj Sakargaye (client communication and milestone tracking) |
| Tools | GitHub, Notion (sprint tracker), Slack, Figma (design reference), Google Meet, Loom |

STAGE 9 QA, UAT AND CLIENT REVIEW Catch every issue before the founder does.

| Objective | Ship a product that works, not a product that demos. Internal QA runs first. UAT gives the founder structured access to test. Both must fully clear before app store submission. |
| --- | --- |
| Internal QA | - Functional testing: every screen, every button, every user flow against the approved Figma file. - Cross-device testing: iOS and Android on current OS version and one major version back. Multiple screen sizes including the smallest supported device. - Edge case testing: empty states, error handling, network failure states, very long text inputs, zero-state screens for new users. - Performance benchmarks: app load time under 3 seconds on a standard connection, scroll at 60fps, API response times logged. - Auth and data security review: authentication flows, session handling, sensitive data storage checks. - Bug Log in Notion: P1 (blocking), P2 (major), P3 (minor). All P1 and P2 bugs are fixed before UAT begins. |
| UAT and Client Review | - Send the founder a TestFlight link (iOS) and APK or internal test track (Android). - Send the UAT Guide in Notion: what to test, how to report issues (screenshot plus written description), and the feedback deadline (5 business days). - Collect all UAT feedback in the shared Notion UAT Log. Each item: screen name, description, screenshot, severity level. - Fix all in-scope bugs reported during UAT. New features or out-of-scope items raised during UAT go through the Change Request process, not directly into the sprint. - Final QA sign-off: Naman confirms the build is release-ready. Abhiraj collects written UAT approval from the founder (Slack message is sufficient). |
| Inputs | Sprint 4 build, QA Checklist, UAT Guide template in Notion |
| Outputs | Completed bug log, fixed and release-ready build, written UAT approval from founder |
| Ownership | Naman Barkiya and Adarsh Pandey (QA execution), Abhiraj Sakargaye (UAT client communication and approval) |
| Tools | Notion (bug log, UAT log), TestFlight, Firebase App Distribution or Google Play internal test track, Slack |

STAGE 10 DELIVERY, HANDOFF AND POST-LAUNCH Ship, hand over everything the founder owns, support, close.

| Objective | Get the app live on both stores, transfer full ownership of all project assets to the founder, and close the engagement with no loose ends. |
| --- | --- |
| App Store Submission | - Prepare the App Store listing: screenshots in all required sizes, short description, full description, keywords, and app category. Abhiraj leads the copy. - The founder must have an active Apple Developer account ($99/year) and a Google Play Developer account ($25 one-time) before submission begins. - Submit to Apple App Store and Google Play Store. Plan for review windows: Apple standard is 1 to 3 days, up to 7 days for first-time submissions. Google Play is 1 to 3 days for new apps. |
| Handoff Package | - Figma files: complete design system and all screens. Ownership transferred to the founder's Figma account. - Codebase: GitHub repository access transferred to the founder's GitHub account. Repository is clean, has a README, and all branches are in order. - Documentation: architecture overview, API documentation, third-party service list with setup notes. - Credentials: all service accounts, API keys, and app store credentials transferred via a 1Password share link or agreed secure method. No credentials in plain text. - Loom walkthrough: a 20 to 30 minute recorded walkthrough of the codebase and architecture, made for the founder's future development team. - Collect the final 30% payment before transferring any credentials or code access. |
| Closure | - Send the Engagement Closure Note to the founder: what was built, what was explicitly left out, and recommended priorities for the next 90 days. - Internal retro: Naman and Abhiraj conduct a 30-minute retro in Notion within one week of delivery. What went well, what to improve, what to do differently next time. - Update Notion project status to "Delivered". Archive the full project record. |
| Post-Launch Support | - 2-week post-launch support window is included in all projects at no extra charge. - P1 bugs (blocking) fixed within 24 hours. P2 bugs fixed within 72 hours during the support window. - P3 bugs, new features, and any new scope are billed separately or moved to the Optimise Retainer. |
| Optimise Retainer | Abhiraj presents retainer options in the Engagement Closure Note. The retainer covers ongoing monitoring, performance tuning, feature iteration, A/B testing, and growth analytics on a monthly basis. |
| Testimonial | Abhiraj requests a testimonial from the founder via Slack within 1 week of launch. If the founder agrees to a case study, log it in the Portfolio Pipeline in Notion. |
| Inputs | Release-ready build, full project asset inventory, final payment received |
| Outputs | Live app on App Store and Play Store, complete handoff package delivered, final payment collected, engagement closed in Notion, internal retro completed |
| Ownership | Naman Barkiya (technical handoff, Loom walkthrough), Abhiraj Sakargaye (app store listing, payment collection, closure communication, testimonial request) |
| Tools | Notion, GitHub, Figma, Apple App Store Connect, Google Play Console, Loom, 1Password, Gmail |

# Appendix A

## Process Flow Diagram

The ten stages below run in sequence. Each stage gate must clear before the next begins. Two controlled overlaps exist: Scoping and Proposal may overlap by 1 to 2 days on simple projects. Design and Development may overlap during Sprint 1 only, where auth and navigation work can start while secondary screens are still being finalised.

| 1 Inbound | > | 2 Qualify | > | 3 Discovery | > | 4 Scoping | > | 5 Proposal |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| v |  |  |  |  |  |  |  |  |  |
| 6 Onboarding | > | 7 Design | > | 8 Dev | > | 9 QA & UAT | > | 10 Delivery |  |

Stage gates: a stage is complete only when all outputs are logged in Notion and relevant sign-offs are recorded. Ownership is always one named person, even when a team works on the stage.

# Appendix B

## Timeline Reference

All timelines run from the date of first email to app store delivery. Stages 1 through 4 (inbound to scoping) typically account for 1 to 2 weeks. Stage 7 (design) adds 2 to 3 weeks. Stages 8 and 9 (development and QA) make up the remainder. App store review windows are not within our control and must be built into every delivery estimate.

| App Complexity | Timeline (Email to Delivery) | Key Conditions for This Range |
| --- | --- | --- |
| Lean MVP: 3 to 5 core screens, single platform, simple auth, basic backend | 8 to 10 weeks | Founder reviews within 48 hours, no third-party API dependencies, iOS or Android only, no admin panel required |
| Standard MVP: 6 to 10 screens, custom APIs, admin panel, dual platform | 10 to 14 weeks | Standard 48-hour review turnaround, moderate backend complexity, basic admin functionality, iOS and Android |
| Complex MVP: AI features, real-time data, multi-role users, multiple integrations | 14 to 20 weeks | AI or ML components, real-time infrastructure, multiple external API integrations, custom admin dashboard, iOS and Android |

Timeline extends when:

- Scope additions are requested mid-project: add 1 to 3 weeks per major addition, raised as a formal Change Request in Notion

- Founder feedback turnaround exceeds 5 business days: each delayed review round adds a 1-week buffer to the project timeline

- Third-party API providers are slow or change specifications mid-project: not within our control; documented in the project record

- Apple App Store review is extended: standard is 1 to 3 days, worst case is 7 or more days for first-time submissions

- Legal or compliance requirements are discovered mid-project: timeline and scope are renegotiated at that point with a signed Change Request

# Appendix C

## Communication Cadence

### Weekly Rhythm

- Monday: Sprint kickoff note in Slack from Naman. Lists what gets built this week and any decisions or assets needed from the founder.

- Wednesday: Async mid-week update in Slack if anything is blocked or a same-day founder decision is needed. Not required if the sprint is on track.

- Friday: 30-minute live demo on Google Meet, or a Loom video walkthrough if the founder cannot attend. Founder logs feedback in the Notion Sprint Review Log by the following Monday.

### Channel Rules

- Slack: daily questions, quick updates, and blockers that need same-day answers. Response target: within 4 hours during working hours (9am to 7pm IST).

- Notion: all review feedback, decisions that affect scope or timeline, milestone sign-offs, and all project documentation. If it matters, it is written in Notion.

- Google Meet: real-time calls only. Sprint demos, kick-off, discovery, and any conversation where text creates confusion.

- Loom: async video for sprint demo recordings, architecture walkthroughs, and complex feedback that is easier to show than type.

- Email: contracts, proposals, and formal external communications only. All operational conversation lives in Slack.

### Escalation

- A blocker not resolved within 24 hours: Abhiraj calls the founder directly. It does not stay in Slack.

- Founder unresponsive at a critical review point for 5 or more business days: the sprint pauses, the timeline extends by the duration of the delay, and this is documented in the Notion project record with a timestamp.

- Scope dispute: both co-founders join the founder on a call within 48 hours. Scope disputes are not resolved over text.